## 20-Year CIP Full (hidden)
COLLINS PARK WATER TREATMENT PLANT - 20 YEAR MASTER PLAN AND NEEDS ASSESSMENT
TOLEDO, OHIO
20-Year CIP Implementation Schedule
Item | Item Description | Priority | Project Duration (years) | Total Estimated Project Cost (2011 dollars) | Year
[5 empty] | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032
[5 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Floc/Sed and Filter Area Roof Immediate Structural Improvements | 1 | 2 | 4950000 | Year 2012 0: #REF!; Year 2013 1: #REF! | #REF!
2 | Chlorination System Improvements | 1 | 3 | 5827000 | Year 2012 0: #REF!; Year 2013 1: #REF!; Year 2014 2: #REF! | #REF!
3 | New SCADA System | 1 | 2 | 8308000 | Year 2012 0: #REF!; Year 2013 1: #REF! | #REF!
4 | Flocculation/Sedimentation and Filter Addition | 1 | 6 | 96600000 | Year 2013 1: #REF!; Year 2014 2: #REF!; Year 2015 3: #REF!; Year 2016 4: #REF!; Year 2017 5: #REF!; Year 2018 6: #REF! | #REF!
5 | Administration Building Expansion/Improvements | 1 | 3 | 1854000 | Year 2013 1: #REF!; Year 2014 2: #REF!; Year 2015 3: #REF! | #REF!
6 | Heatherdowns Pump Station Immediate Improvements | 2 | 3 | 2552000 | Year 2014 2: #REF!; Year 2015 3: #REF!; Year 2016 4: #REF! | #REF!
7 | Low Service Pump Station Short-Term Improvements | 2 | 3 | 17094000 | Year 2015 3: #REF!; Year 2016 4: #REF!; Year 2017 5: #REF! | #REF!
8 | General Water Treatment Plant HVAC Improvements | 2 | 2 | 1869000 | Year 2016 4: #REF!; Year 2017 5: #REF! | #REF!
9 | Lime/Soda Ash Storage and Feed System Rehabilitation and Improvements | 2 | 3 | 3344000 | Year 2016 4: #REF!; Year 2017 5: #REF!; Year 2018 6: #REF! | #REF!
10 | High Service Pump Station Miscellaneous Improvements | 2 | 3 | 4470000 | Year 2016 4: #REF!; Year 2017 5: #REF!; Year 2018 6: #REF! | #REF!
11 | Waste Washwater Facility Short-Term Improvements | 2 | 2 | 2132000 | Year 2016 4: #REF!; Year 2017 5: #REF! | #REF!
12 | Plant-Wide Power Improvements | 2 | 3 | 4245000 | Year 2017 5: #REF!; Year 2018 6: #REF!; Year 2019 7: #REF! | #REF!
13 | Raw Water Intake Improvements | 2 | 2 | 1775000 | Year 2017 5: #REF!; Year 2018 6: #REF! | #REF!
14 | Residuals Handling and Dewatering Rehabilitation and Improvements | 2 | 3 | 9965000 | Year 2017 5: #REF!; Year 2018 6: #REF!; Year 2019 7: #REF! | #REF!
15 | Miscellaneous Chemical Storage and Feed System Improvements | 2 | 3 | 4540000 | Year 2017 5: #REF!; Year 2018 6: #REF!; Year 2019 7: #REF! | #REF!
16 | Filter and Pipe Gallery Short-Term Improvements | 3 | 5 | 32973000 | Year 2019 7: 4945950; Year 2020 8: 7006762.5; Year 2021 9: 7006762.5; Year 2022 10: 7006762.5; Year 2023 11: 7006762.5 | 32973000
17 | Flocculation/Sedimentation Basin and Clearwell Rehabilitation | 3 | 7 | 14321000 | Year 2019 7: 2148150; Year 2020 8: 2028808.3333; Year 2021 9: 2028808.3333; Year 2022 10: 2028808.3333; Year 2023 11: 2028808.3333; Year 2024 12: 2028808.3333; Year 2025 13: 2028808.3333 | 14321000
18 | Low Service Pump Station Mid-Term Improvements | 3 | 1 | 2289000 | Year 2020 8: #REF! | #REF!
19 | Intermediate Architectural/Structural Repairs | 3 | 3 | 2638000 | Year 2021 9: #REF!; Year 2022 10: #REF!; Year 2023 11: #REF! | #REF!
20 | Filter System Long-Term Improvements | 4 | 4 | 187000 | Year 2023 11: #REF!; Year 2024 12: #REF!; Year 2025 13: #REF!; Year 2026 14: #REF! | #REF!
21 | Residuals Handling and Dewatering Facility Expansion | 4 | 3 | 10577000 | Year 2025 13: #REF!; Year 2026 14: #REF!; Year 2027 15: #REF! | #REF!
22 | Pumping Equipment Improvements | 4 | 2 | 8105000 | Year 2027 15: #REF!; Year 2028 16: #REF! | #REF!
23 | Heatherdowns Pump Station Long-Term Improvements | 5 | 2 | 2978000 | Year 2029 17: #REF!; Year 2030 18: #REF! | #REF!
|  |  | TOTALS | 243593000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | #REF!
|  |  |  | Annual Cost (in Millions) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0
|  |  |  | Cummulative Annual Cost (in Millions) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## 20-Year CIP Condensed
COLLINS PARK WATER TREATMENT PLANT - 20 YEAR MASTER PLAN AND NEEDS ASSESSMENT
TOLEDO, OHIO
20-Year CIP Implementation Schedule
Item | Item Description | Priority | Project Duration (years) | Total Estimated Project Cost (2012 dollars) | Year
[5 empty] | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 - 2027 | 2028 - 2032
[5 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 - 15 | 16 - 20
1 | Floc/Sed and Filter Area Roof Immediate Structural Improvements | 1 | 3 | 15000000 | Year 2012 0: 2550000; Year 2013 1: 6225000; Year 2014 2: 6225000 |  |  | 15000000
2 | Chlorination System Improvements | 1 | 3 | 8000000 | Year 2012 0: 430000; Year 2013 1: 2300000; Year 2014 2: 5270000 |  |  | 8000000
3 | New SCADA System | 1 | 2 | 5000000 | Year 2013 1: 2500000; Year 2014 2: 2500000 |  |  | 5000000
4 | Flocculation/Sedimentation and Filter Addition Basin 7 | 1 | 5 | 53400000 | Year 2013 1: 800000; Year 2014 2: 10400000; Year 2015 3: 20500000; Year 2016 4: 21700000 |  |  | 53400000
5 | Flocculation/Sedimentation and Filter Addition Basin 8 | 1 | 5 | 43200000 | Year 2013 1: 600000; Year 2014 2: 9800000; Year 2015 3: 17000000; Year 2016 4: 15800000 |  |  | 43200000
6 | Administration Building Expansion/Improvements (includes Maintenance Shop/Stockroom project) | 1 | 3 | 4804000 | Year 2013 1: 1350000; Year 2014 2: 1200000; Year 2015 3: 2254000 |  |  | 4804000
7 | Heatherdowns Pump Station Immediate Improvements | 2 | 3 | 2552000 | Year 2013 1: 382800; Year 2014 2: 1276000; Year 2015 3: 893200 |  |  | 2552000
8 | Low Service Pump Station Improvements (includes LSPS Security Project) | 2 | 4 | 18344000 | Year 2012 0: 50000; Year 2013 1: 2200000; Year 2014 2: 6400000; Year 2015 3: 9694000 |  |  | 18344000
9 | General Water Treatment Plant HVAC Improvements | 2 | 2 | 1869000 | Year 2016 4: 280350; Year 2017 5: 1588650 |  |  | 1869000
10 | Lime/Soda Ash Storage and Feed System Rehabilitation and Improvements | 2 | 3 | 3344000 | Year 2016 4: 501600; Year 2017 5: 1672000; Year 2018 6: 1170400 |  |  | 3344000
11 | High Service Pump Station Miscellaneous Improvements | 2 | 4 | 4470000 | Year 2013 1: 520000; Year 2016 4: 670500; Year 2017 5: 2000000; Year 2018 6: 1279500 |  |  | 4470000
12 | Waste Washwater Facility Short-Term Improvements | 2 | 2 | 2132000 | Year 2016 4: 319800; Year 2017 5: 1812200 |  |  | 2132000
13 | Plant-Wide Power Improvements | 2 | 3 | 7000000 | Year 2012 0: 50000; Year 2013 1: 2450000; Year 2014 2: 4500000 |  |  | 7000000
14 | Raw Water Intake Improvements | 2 | 2 | 1775000 | Year 2017 5: 266250; Year 2018 6: 1508750 |  |  | 1775000
15 | Residuals Handling and Dewatering Rehabilitation and Improvements | 2 | 3 | 9965000 | Year 2017 5: 1494750; Year 2018 6: 4982500; Year 2019 7: 3487750 |  |  | 9965000
16 | Miscellaneous Chemical Storage and Feed System Improvements | 2 | 3 | 4540000 | Year 2017 5: 681000; Year 2018 6: 2270000; Year 2019 7: 1589000 |  |  | 4540000
17 | Filter and Pipe Gallery Short-Term Improvements (includes Backup Backwash Supply/Plant Water Loop project) | 3 | 7 | 34973000 |  | 1600000 | 1600000 |  | 2747750 | 7256313 | 7256313 | 7256313 | 7256311 |  |  |  |  | 34973000
18 | Flocculation/Sedimentation Basin and Clearwell Rehabilitation | 3 | 7 | 14321000 |  |  | 1200000 | 2186833 | 2186833 | 2186833 | 2186833 | 2186833 | 2186833 |  |  |  |  | 14320998
19 | Low Service Pump Station Mid-Term Improvements | 3 | 1 | 2289000 | Year 2020 8: 2289000 |  |  | 2289000
20 | Intermediate Architectural/Structural Repairs | 3 | 3 | 2638000 | Year 2021 9: 395700; Year 2022 10: 1319000 | 923300 |  | 2638000
21 | Filter System Long-Term Improvements | 4 | 4 | 187000 | [11 empty] | 187000 |  | 187000
22 | Residuals Handling and Dewatering Facility Expansion | 4 | 3 | 10577000 | Year 2017 5: 10577000 |  |  | 10577000
23 | Pumping Equipment Improvements | 4 | 2 | 8105000 | Year 2019 7: 1215750; Year 2020 8: 6889250 |  |  | 8105000
24 | Heatherdowns Pump Station Long-Term Improvements | 5 | 2 | 2978000 | Year 2021 9: 2978000 |  |  | 2978000
25 | Alum Storage | 1 | 2 | 2500000 | Year 2013 1: 1250000; Year 2014 2: 1250000
20 YEAR MASTER PLAN SUBTOTALS |  |  |  | 263963000 | 3080000 | 22177800 | 51621000 | 52528033 | 44206833 | 29534996 | 20654296 | 15735646 | 18621394 | 3373700 | 1319000 | 1110300 | 0